# Program Action Plan- Example

Program Name: Basket Weaving

Last Completed Program Review Date: 2014-2016

Next Program Review Date: 2022-2024

Action Plan:

| Goal: Revamp Curriculum |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action Item: | Timeline: | Measure: | Lead: | Map to Institutional Goal: | Status: |
| Revise Program Goals | F16 | Hold 2 half day faculty retreats to develop or edit 3-4 program goals | Weave, Strand | Deepen Academic Excellence | In progress |
| Increase UG research opportunities | F19 | Work with CASL Director of UG and GR Research to develop initiative | Bill | Deepen Academic Excellence, Student Engagement & Success | Future |
| Create & Implement Capstone course | By F21 | Develop capstone course that allows students to take part in service & community learning | Wicker | Student Engagement & Success, Metro Impact | Future |

| Goal: Build community & program identity |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action Item: | Timeline: | Measure: | Lead: | Map to Institutional Goal: | Status: |
| Increase prospective & FY student outreach | S17 | Hold info tables at 3 summer orientation sessions | Plait | Enrollment & Funding | Future |
| Increase social media outreach | F16 | Work with University marketing & communications to develop marketing plan to promote program | Bill | Enrollment & Funding | Completed |
| Alumni Speaker Series | By F19 | Bring at least one alumni speaker a semester to meet with student club and UM-D community | Weave | Student Engagement & Success, Metro Impact | In progress |